Cotiviti Practicum – Fall 2026

MS in Biomedical Informatics w/ emphasis in Data Science and AI.

Tara Allred

Timeline: August 24th- December 11th 2026

Practicum Requirements: 180-200 hours

Cotiviti Team Meetings: Thursday’s at 130pm MST.

U of U Breaks : No meetings

·      Fall Break: October 10-18th

·      Thanksgiving: November 26-29th

Initial Dataset

CMS Medicare Post-Acute Care Utilization – Inpatient Rehabilitation Facility by Geography and Provider

Project Approach:

Data Problem Research Question Hypothesis Analysis Evidence Conclusion

Phase 1: August 24th – September 11th

·      Dataset exploration + Research Question Development

·      Cotiviti Feedback

o   What findings are meaningful from an industry perspective?

o   What questions are worth pursuing?

o   What am I not seeing?

o   What additional AI tools would be helpful?

Phase 2: Sep 14th-October 9th

·      Data Preparation and Data Analysis

o   Clean data

o   Add additional datasets where needed

o   Develop initial visualizations.

·      Cotiviti Feedback

o   Do findings support the research question?

o   Should the Hypothsis be refined?

o   Is anything missing?

o   How would Cotiviti tackle this in a way that I am not seeing?

·      Milestone: analysis ready dataset, and research question finalized.

FALL BREAK: OCT-10th-18th – NO CLASS OR MEETINGS

Phase 3: Oct 19th – Nov 6th

·      Testing the research question

o   Engineer features

o   Apply appropriate statistical data and/or methods.

o   Test the hypothesis

o   Evaluate significance and investigate further

·      Cotiviti Feedback

o   Are the results being interpreted correctly?

o   Are these findings meaningful to Cotiviti? How would you proceed?

o   What additional analysis would help here?

Phase 4: Nov 9th – Nov 25th

·      Results and Validation

o   Refine and validate the results

o   Find similar research

o   Investigate alternative explanations

o   Biases?

o   Develop and fine tune Visualizations

o   Does the evidence support the hypothesis?

·      Cotiviti Feedback

o   What conclusions are supported?

o   What additional tools or methods can be used to reach a conclusion?

o   What are the limitations? Can you work around them?

o   How could findings translate into a similar project with Cotiviti?

THANKSGIVING BREAK Nov 26th-29th  NO CLASS OR MEETINGS

Nov 30th -Dec 11th

·      Final Paper and Analysis + Capstone Direction

o   EDIT!

o   Summarize question, methods, results and conclusions.

o   Create PP presentation.

o   Incorporate Cotiviti Feedback

·      Cotiviti Feedback

o   Is the project story clear?

o   Are conclusions supported by evidence?

o   Take away? Good/Bad

o   What could have been done differently and what worked well?